## Estimation Phase
3930.378 |  | Total Development Effort |  |  | 1723.85 | 0 | 0 | iOS Buffer | 0.3 |  |  |  |  | 0
|  | QA Estimation |  |  | 689.54 | 0 | 0 | iOS Buffer BG Service | 0.5 |  |  |  |  | 0
|  | PM Hours |  | 20% | 482.678 | 0 | 0 | [6 empty] | 0
1179.1134 |  | Design Arch |  | 25% | 430.9625 | 0 | 0 | [6 empty] | 0
|  | Spec + UI/UX |  | 15% | 258.5775 | 0 | 0 | [6 empty] | 0
|  | Development Buffer | 20% | 20% | 344.77
Milestones | Module | Sub Module | Screen Id / Feature Id | Module | Total Estimation | Data Model |  |  | API, Validation |  |  | Business Rules |  |  | UI |  |  | Fixed Hours | Total Estimation | Complexity (%) | Unit Testing (%) | Rework (%) | Total Dev | QA |  |  | Total QA (40%) | Total Estimation
[6 empty] | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | [6 empty] | Plan | Execution | Regression
[6 empty] | 1 | 2 | 3 | 1 | 3 | 6 | 3 | 6 | 12 | 4 | 10 | 15 |  |  | 2 | 5 | 10 |  | 12 | 16 | 12
| Landing Page | Landing Page |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Login Page |  |  | 6.44 | [12 empty] | 4 | 4 |  | 0.2 | 0.4 | 4.6 | 0.552 | 0.736 | 0.552 | 1.84 | 6.44
| User Profile | Change Password |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Change Language |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Sub-User Management |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Logout |  |  | 6.44 | [12 empty] | 4 | 4 |  | 0.2 | 0.4 | 4.6 | 0.552 | 0.736 | 0.552 | 1.84 | 6.44
| Dashboard | Vehicle Status Summary |  | Total Vehicles | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  |  |  | Running / Stopped / Idle / Offline | 35.42 | 2 |  |  | 2 |  |  | 2 |  |  | 3 |  |  | 0 | 22 |  | 1.1 | 2.2 | 25.3 | 3.036 | 4.048 | 3.036 | 10.12 | 35.42
|  |  |  | Not Assigned to Job | 20.93 | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 13 |  | 0.65 | 1.3 | 14.95 | 1.794 | 2.392 | 1.794 | 5.98 | 20.93
|  | Distance Analytics |  | Total Distance Covered | 20.93 | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 13 |  | 0.65 | 1.3 | 14.95 | 1.794 | 2.392 | 1.794 | 5.98 | 20.93
|  |  |  | Average Distance per Vehicle | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  | Job Assignment Summary |  | Job Assigned Vehicles Count | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | Job Not Assigned Vehicles Count | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
| Tracking | Map View |  | Live map visualization | 91.77 | 3 |  |  | 1 |  |  | 1 |  |  |  | 5 |  | 0 | 57 |  | 2.85 | 5.7 | 65.55 | 7.866 | 10.488 | 7.866 | 26.22 | 91.77
|  |  |  | Display geofences and pickup points | 98.21 | 3 |  |  | 3 |  |  | 1 | 2 |  |  | 4 |  | 0 | 61 |  | 3.05 | 6.1 | 70.15 | 8.418 | 11.224 | 8.418 | 28.06 | 98.21
|  |  |  | Vehicle route display upon selection | 90.16 | 1 |  |  | 1 |  |  |  | 4 |  |  | 3 |  | 0 | 56 |  | 2.8 | 5.6 | 64.4 | 7.728 | 10.304 | 7.728 | 25.76 | 90.16
|  | Job-Based Tracking |  | Job Category Selection: Upcoming /In Progress /Completed /Failed /Total | 86.94 | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  | 0 | 54 |  | 2.7 | 5.4 | 62.1 | 7.452 | 9.936 | 7.452 | 24.84 | 86.94
|  |  |  | Ward / Zone / Vehicle Number selection | 86.94 | 2 |  |  | 4 |  |  |  | 3 |  |  | 3 |  | 0 | 54 |  | 2.7 | 5.4 | 62.1 | 7.452 | 9.936 | 7.452 | 24.84 | 86.94
|  |  |  | Direct Vehicle Number search bar | 45.08 | 1 |  |  | 1 |  |  |  | 3 |  | 2 |  |  | 0 | 28 |  | 1.4 | 2.8 | 32.2 | 3.864 | 5.152 | 3.864 | 12.88 | 45.08
|  | Vehicle-Based Tracking |  | Status Categories: On Job/Off Job/Not Assigned/Completed/Not Deployed/Total | 91.77 | 2 |  |  | 3 |  |  |  | 2 |  |  | 4 |  | 0 | 57 |  | 2.85 | 5.7 | 65.55 | 7.866 | 10.488 | 7.866 | 26.22 | 91.77
|  |  |  | Town / Zone / Ward selection | 86.94 | 3 |  |  | 3 |  |  |  | 3 |  |  | 3 |  | 0 | 54 |  | 2.7 | 5.4 | 62.1 | 7.452 | 9.936 | 7.452 | 24.84 | 86.94
|  | Collection Point-Based Tracking |  | Collection Point List | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | On selection, display: pickup date/time, Vehicle number | 99.82 | 2 |  |  | 2 |  |  |  | 3 |  |  | 4 |  | 0 | 62 |  | 3.1 | 6.2 | 71.3 | 8.556 | 11.408 | 8.556 | 28.52 | 99.82
|  | Geofence Management |  | Geofence creation | 74.06 | 2 |  |  | 1 |  |  | 1 |  |  |  | 4 |  | 0 | 46 |  | 2.3 | 4.6 | 52.9 | 6.348 | 8.464 | 6.348 | 21.16 | 74.06
|  |  |  | View created geofences: Town-wise/Zone-wise/Ward-wise/Overall view | 96.6 | 2 |  |  |  | 3 |  | 3 |  |  |  | 4 |  | 0 | 60 |  | 3 | 6 | 69 | 8.28 | 11.04 | 8.28 | 27.6 | 96.6
| Reports | Job Reports |  | Simple Report - 3 | 41.86 | 2 |  |  | 2 |  |  | 2 |  |  | 4 |  |  | 0 | 26 |  | 1.3 | 2.6 | 29.9 | 3.588 | 4.784 | 3.588 | 11.96 | 41.86
|  |  |  | Medium Report - 3 | 67.62 | 2 |  |  | 2 |  |  | 2 |  |  | 8 |  |  | 0 | 42 |  | 2.1 | 4.2 | 48.3 | 5.796 | 7.728 | 5.796 | 19.32 | 67.62
|  |  |  | Complex Report - 4 | 96.6 |  |  | 4 | 2 |  |  | 2 |  |  | 10 |  |  | 0 | 60 |  | 3 | 6 | 69 | 8.28 | 11.04 | 8.28 | 27.6 | 96.6
| Settings |  |  |  | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Company Management |  | Company List | 22.54 | [12 empty] | 14 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | New Company Creation | 40.25 | 1 |  |  | 1 |  |  | 1 |  |  |  | 2 |  | 0 | 25 |  | 1.25 | 2.5 | 28.75 | 3.45 | 4.6 | 3.45 | 11.5 | 40.25
|  |  |  | Company Configuration | 20.93 | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 13 |  | 0.65 | 1.3 | 14.95 | 1.794 | 2.392 | 1.794 | 5.98 | 20.93
|  | Company Sub-User Management |  | Sub-User List | 24.15 | 2 |  |  | 2 |  |  | 1 |  |  | 2 |  |  |  | 15 |  | 0.75 | 1.5 | 17.25 | 2.07 | 2.76 | 2.07 | 6.9 | 24.15
|  |  |  | Sub-User Creation | 12.88 | [12 empty] | 8 | 8 |  | 0.4 | 0.8 | 9.2 | 1.104 | 1.472 | 1.104 | 3.68 | 12.88
|  |  |  | Role & Permission Assignment | 25.76 | 3 |  |  | 2 |  |  | 1 |  |  | 2 |  |  |  | 16 |  | 0.8 | 1.6 | 18.4 | 2.208 | 2.944 | 2.208 | 7.36 | 25.76
|  | Branch Management |  | Branch List | 24.15 | 2 |  |  | 2 |  |  | 1 |  |  | 2 |  |  |  | 15 |  | 0.75 | 1.5 | 17.25 | 2.07 | 2.76 | 2.07 | 6.9 | 24.15
|  |  |  | Branch Creation & Mapping | 25.76 | 1 |  |  | 1 |  |  | 2 |  |  | 2 |  |  |  | 16 |  | 0.8 | 1.6 | 18.4 | 2.208 | 2.944 | 2.208 | 7.36 | 25.76
|  | Collector Management |  | Collector List | 24.15 | 2 |  |  | 2 |  |  | 1 |  |  | 2 |  |  |  | 15 |  | 0.75 | 1.5 | 17.25 | 2.07 | 2.76 | 2.07 | 6.9 | 24.15
|  |  |  | Collector Creation & Assignment | 38.64 | 2 |  |  | 2 |  |  |  | 2 |  | 2 |  |  |  | 24 |  | 1.2 | 2.4 | 27.6 | 3.312 | 4.416 | 3.312 | 11.04 | 38.64
|  | Area Management |  | Town Management | 28.98 |  |  | 2 | 1 |  |  | 1 |  |  | 2 |  |  |  | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Zone Management | 28.98 |  |  | 2 | 1 |  |  | 1 |  |  | 2 |  |  |  | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Ward Management | 28.98 |  |  | 2 | 1 |  |  | 1 |  |  | 2 |  |  |  | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Area Creation & Management | 28.98 |  |  | 2 | 1 |  |  | 1 |  |  | 2 |  |  |  | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  | Vehicle Management |  | Vehicle List | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | New Vehicle Addition | 12.88 | [12 empty] | 8 | 8 |  | 0.4 | 0.8 | 9.2 | 1.104 | 1.472 | 1.104 | 3.68 | 12.88
|  |  |  | Vehicle Group Creation | 12.88 | [12 empty] | 8 | 8 |  | 0.4 | 0.8 | 9.2 | 1.104 | 1.472 | 1.104 | 3.68 | 12.88
|  |  |  | Group-wise Vehicle Assignment | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  | Driver Management |  | Driver List | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | New Driver Addition | 12.88 | [12 empty] | 8 | 8 |  | 0.4 | 0.8 | 9.2 | 1.104 | 1.472 | 1.104 | 3.68 | 12.88
|  | Alert Management |  | Alert Creation | 27.37 | 2 |  |  | 1 |  |  | 2 |  |  | 2 |  |  |  | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  |  |  | Alert Assignment to Vehicles / Drivers | 28.98 | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  |  | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Alert Reminder Rules | 14.49 | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  |  | 9 |  | 0.45 | 0.9 | 10.35 | 1.242 | 1.656 | 1.242 | 4.14 | 14.49
|  | Collection Area Management |  | Collection Area List | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | Collection Area Creation | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | Collection Address Management | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | Collection Address Group Management | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  | Job Management |  | Job Creation and Configuration | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | Job Penalty Configuration | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  | Expense Management |  | Expense Creation and Configuration | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  | Address Management |  | Address Addition and Maintenance | 37.03 | 2 |  |  | 1 |  |  |  | 2 |  | 2 |  |  |  | 23 |  | 1.15 | 2.3 | 26.45 | 3.174 | 4.232 | 3.174 | 10.58 | 37.03
|  | Geofence Management |  | Geofence List | 25.76 | 3 |  |  | 2 |  |  | 1 |  |  | 2 |  |  |  | 16 |  | 0.8 | 1.6 | 18.4 | 2.208 | 2.944 | 2.208 | 7.36 | 25.76
|  |  |  | Geofence Creation | 62.79 | 3 |  |  | 4 |  |  |  | 4 |  | 2 |  |  |  | 39 |  | 1.95 | 3.9 | 44.85 | 5.382 | 7.176 | 5.382 | 17.94 | 62.79
|  |  |  | Geofence Group Management | 61.18 | 3 |  |  | 3 |  |  |  |  | 2 | 2 |  |  |  | 38 |  | 1.9 | 3.8 | 43.7 | 5.244 | 6.992 | 5.244 | 17.48 | 61.18
|  | Route Management |  | Route List | 22.54 | 2 |  |  | 1 |  |  | 1 |  |  | 2 |  |  |  | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
|  |  |  | New Route Creation | 70.84 | 3 |  |  |  | 1 |  |  | 3 |  |  | 2 |  |  | 44 |  | 2.2 | 4.4 | 50.6 | 6.072 | 8.096 | 6.072 | 20.24 | 70.84
|  | Device Management |  | Device Assignment and Configuration | 41.86 | 2 |  |  | 1 |  |  | 1 |  |  |  | 2 |  |  | 26 |  | 1.3 | 2.6 | 29.9 | 3.588 | 4.784 | 3.588 | 11.96 | 41.86
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Note on S7: Anandan Shanmugam: Enter 16 for 25 Hrs Enter 6.3 for 10 Hrs Enter 16 for 25 Hrs

## Estimation Mobile
937.9032 |  | Total Development Effort |  |  | 411.7 | 0 | 0 | iOS Buffer | 0.5 |  |  |  |  | 0
|  | QA Estimation |  |  | 164.036 | 0 | 0 | iOS Buffer BG Service | 0.5 |  |  |  |  | 0
|  | PM Hours |  | 20% | 115.1472 | 0 | 0 | [6 empty] | 0
468.9516 |  | Design Arch |  | 25% | 102.925 | 0 | 0 | [6 empty] | 0
|  | Spec + UI/UX |  | 15% | 61.755 | 0 | 0 | [6 empty] | 0
|  | Development Buffer | 20% | 20% | 82.34
Milestones | Module | Sub Module | Screen Id / Feature Id | Module | Total Estimation | Data Model |  |  | API, Validation |  |  | Business Rules |  |  | UI |  |  | Fixed Hours | Total Estimation | Complexity (%) | Unit Testing (%) | Rework (%) | Total Dev | QA |  |  | Total QA (40%) | Total Estimation
[6 empty] | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | Simple | Medium | Complex | [6 empty] | Plan | Execution | Regression
[6 empty] | 1 | 2 | 3 | 1 | 3 | 6 | 3 | 6 | 12 | 4 | 10 | 15 |  |  | 2 | 5 | 10 |  | 12 | 16 | 12
| Landing Page | Splash Page |  |  | 6.44 | [12 empty] | 4 | 4 |  | 0.2 | 0.4 | 4.6 | 0.552 | 0.736 | 0.552 | 1.84 | 6.44
|  | Login Page |  |  | 6.44 | [12 empty] | 4 | 4 |  | 0.2 | 0.4 | 4.6 | 0.552 | 0.736 | 0.552 | 1.84 | 6.44
| User Profile | Change Password |  |  | 2.576 | [12 empty] | 2 | 2 |  | 0.1 | 0.2 | 2.3 |  |  | 0.276 | 0.276 | 2.576
|  | Change Language |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Sub-User Management |  |  | 4.83 | [12 empty] | 3 | 3 |  | 0.15 | 0.3 | 3.45 | 0.414 | 0.552 | 0.414 | 1.38 | 4.83
|  | Logout |  |  | 3.22 | [12 empty] | 2 | 2 |  | 0.1 | 0.2 | 2.3 | 0.276 | 0.368 | 0.276 | 0.92 | 3.22
| Dashboard | Vehicle Status Summary |  | Total Vehicles | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  |  |  | Running / Stopped / Idle / Offline | 35.42 | 2 |  |  | 2 |  |  | 2 |  |  | 3 |  |  | 0 | 22 |  | 1.1 | 2.2 | 25.3 | 3.036 | 4.048 | 3.036 | 10.12 | 35.42
|  |  |  | Not Assigned to Job | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  | Distance Analytics |  | Total Distance Covered | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  |  |  | Average Distance per Vehicle | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  | Job Assignment Summary |  | Job Assigned Vehicles Count | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
|  |  |  | Job Not Assigned Vehicles Count | 27.37 | 1 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 17 |  | 0.85 | 1.7 | 19.55 | 2.346 | 3.128 | 2.346 | 7.82 | 27.37
| Tracking | Map View |  | Live map visualization | 28.98 | 2 |  |  | 1 |  |  | 1 |  |  | 3 |  |  | 0 | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Display geofences and pickup points | 25.76 | 2 |  |  | 3 |  |  | 1 |  |  | 2 |  |  | 0 | 16 |  | 0.8 | 1.6 | 18.4 | 2.208 | 2.944 | 2.208 | 7.36 | 25.76
|  |  |  | Vehicle route display upon selection | 32.2 | 1 |  |  | 1 |  |  | 2 |  |  | 3 |  |  | 0 | 20 |  | 1 | 2 | 23 | 2.76 | 3.68 | 2.76 | 9.2 | 32.2
|  | Job-Based Tracking |  | Job Category Selection: Upcoming /In Progress /Completed /Failed /Total | 33.81 | 1 |  |  | 2 |  |  | 2 |  |  | 3 |  |  | 0 | 21 |  | 1.05 | 2.1 | 24.15 | 2.898 | 3.864 | 2.898 | 9.66 | 33.81
|  |  |  | Ward / Zone / Vehicle Number selection | 35.42 | 2 |  |  | 2 |  |  | 2 |  |  | 3 |  |  | 0 | 22 |  | 1.1 | 2.2 | 25.3 | 3.036 | 4.048 | 3.036 | 10.12 | 35.42
|  |  |  | Direct Vehicle Number search bar | 25.76 | 1 |  |  | 1 |  |  | 2 |  |  | 2 |  |  | 0 | 16 |  | 0.8 | 1.6 | 18.4 | 2.208 | 2.944 | 2.208 | 7.36 | 25.76
|  | Vehicle-Based Tracking |  | Status Categories: On Job/Off Job/Not Assigned/Completed/Not Deployed/Total | 28.98 | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 0 | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  |  |  | Town / Zone / Ward selection | 28.98 | 2 |  |  | 2 |  |  | 2 |  |  | 2 |  |  | 0 | 18 |  | 0.9 | 1.8 | 20.7 | 2.484 | 3.312 | 2.484 | 8.28 | 28.98
|  | Collection Point-Based Tracking |  | Collection Point List | 20.93 | 1 |  |  | 1 |  |  | 1 |  |  | 2 |  |  | 0 | 13 |  | 0.65 | 1.3 | 14.95 | 1.794 | 2.392 | 1.794 | 5.98 | 20.93
|  |  |  | On selection, display: pickup date/time, Vehicle number | 32.2 | 1 |  |  | 2 |  |  | 3 |  |  | 2 |  |  | 0 | 20 |  | 1 | 2 | 23 | 2.76 | 3.68 | 2.76 | 9.2 | 32.2
[5 empty] | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Reports | Job Reports |  | Simple Report - 3 | 16.1 | [12 empty] | 10 | 10 |  | 0.5 | 1 | 11.5 | 1.38 | 1.84 | 1.38 | 4.6 | 16.1
|  |  |  | Medium Report - 3 | 16.1 | [12 empty] | 10 | 10 |  | 0.5 | 1 | 11.5 | 1.38 | 1.84 | 1.38 | 4.6 | 16.1
|  |  |  | Complex Report - 4 | 22.54 | [12 empty] | 14 | 14 |  | 0.7 | 1.4 | 16.1 | 1.932 | 2.576 | 1.932 | 6.44 | 22.54
[5 empty] | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [12 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | 0 | [13 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
Note on S7: Anandan Shanmugam: Enter 16 for 25 Hrs Enter 6.3 for 10 Hrs Enter 16 for 25 Hrs

## Cost Estimation
| Web Phase | 3930
| Mobile | 937
| Total | 4867
| Role | Responsibility | count | Effort (Hours) | % Effort | Rate (₹ / Hour) | Cost (₹) | Name | Rate (₹ / Hour) | Cost (₹)
| Solution Architect | Overall design, architecture, technical reviews | 1 | 243.35 | 5% | 2000 | 486700 | Thiagarajan | 0 | 0
| Backend Developers | Core logic, APIs, tracking engine, AI integration | 2 | 1216.75 | 25% | 1600 | 1946800 | Susil / Prabhu |  | 0
| Frontend Developers | Web admin panels, dashboards, map views | 2 | 973.4 | 20% | 1600 | 1557440 | Thilaga / Kumarasan |  | 0
| QA Engineers | Functional testing, regression, UAT, go-live support | 1 | 243.35 | 5% | 1200 | 292020 | Vimal |  | 0
| Project Manager | Planning, tracking, delivery, stakeholder coordination | 1 | 243.35 | 5% | 2000 | 486700 | Sundar |  | 0
| UI / UX | Wireframes, user journeys, design system | 1 | 194.68 | 4% | 1000 | 194680 | Tharun |  | 0
| Business Analyst (BA) | Requirements, process flows, user stories, UAT support | 1 | 194.68 | 4% | 1200 | 233616 | Maniraja |  | 0
| DevOps | CI/CD, environments, deployments, monitoring | 1 | 194.68 | 4% | 1600 | 311488 | Sankar |  | 0
| Mobile App Developers | Android & iOS app development & integration | 2 | 973.4 | 20% | 1600 | 1557440 | Hariharan / Divya |  | 0
| AI/ML Developer | AI enhancements, prediction logic, smart analytics | 1 | 389.36 | 8% | 1800 | 700848 | Shivaganesh |  | 0
| Total Estimated |  | 13 | 4867 | 100% | 15600 | 7767732 |  | 0 | 0
| Role | Names
| Solution Architect | Thiagarajan
| Backend Developers | Susil / Prabhu
| Frontend Developers | Thilaga / Kumarasan
| QA Engineers | Vimal
| Project Manager | Sundar
| UI / UX | Tharun
| Business Analyst (BA) | Maniraja
| DevOps | Sankar
| Mobile App Developers | Hariharan / Divya
| AI/ML Developer | Shivaganesh
Total Estimated
| Total effort: 5850 hrs (Web 4600 + Mobile 1250) | Internal Execution Cost
| Duration: 5 months (4 Dev + 1 QA/UAT/Go-Live) | Total Hours: 5850
| Counts: Backend (2), Frontend (2), Mobile (2), others (1 each) | Total Internal Cost: ₹33,36,500 (≈ ₹33.3 Lakhs)
| Total price target: ₹40 Lakhs | With 20% Margin
| Required margin: 20% | Margin (20%) ≈ ₹6.7 Lakhs
| Internal execution cost ≈ ₹33.3 Lakhs | Final Project Cost: ≈ ₹40 Lakhs
| Separate Infrastructure Cost | Cloud servers (App + DB + staging): ₹40k / month
| This is not included in the above resource costing. | Map & tracking services / APIs: ₹10k / month
CI/CD, monitoring, storage, backups: ₹10k / month
Estimated Monthly Infra: ₹60,000
For 5 months: ₹3,00,000
Phase-wise Fixed Price
| Web Phase | Duration | Cost (₹ Lakhs)
| Discovery & Design | 3–4 weeks
| Core Development | 4 months
| QA & UAT | 0.5 month
| Go-Live & Stabilization | 0.5 month
| Total Fixed Price | 5 Months
| Mobile Phase | Duration | Cost (₹ Lakhs)
| Discovery & Design | 2–3 weeks
| Core Development | 3 months
| QA & UAT | 0.5 month
| Go-Live & Stabilization | 0.5 month
| Total Fixed Price | 4 Months
| 800 | 1900
| 580 | 1600
| 550 | 1400
| 440 | 1100
| 650 | 2000
| 450 | 1300
| 450 | 1200
| 550 | 1400
| 580 | 1400
| 700 | 1400
Here is the recalculated estimation:
Role | Responsibility | Count | Effort (Hours) | % Effort | Rate (₹/Hour) | Cost (₹)
Solution Architect | Overall design, ownership, reviews | 1 | 263 | 5.7% | 1900 | 499700
Backend Developers | Core logic, tracking engine, APIs | 2 | 1446 | 31.4% | 1600 | 2313600
Frontend Developers | Web admin & dashboards | 2 | 1216 | 26.4% | 1400 | 1702400
QA Engineers | Functional, regression, UAT | 1 | 657 | 14.3% | 1100 | 722700
Project Manager | Planning, tracking, client coordination | 1 | 296 | 6.5% | 2000 | 592000
UI / UX | User journeys, wireframes, design support | 1 | 230 | 5% | 1300 | 299000
Business Analyst (BA) | Requirements, process flows, UAT support | 1 | 230 | 5% | 1200 | 276000
DevOps | Setup, releases, environments | 1 | 263 | 5.7% | 1400 | 368200
New Total